## Sheet1
Process Area | Sprint | User Story Id | User Story Name | Bundle Id | Version | Deployment sheet Name | Comments
P2P | S1 | 74218 | Finance Partner's Access Level to the Requisition | 191463 | 1 | CA P2P Custom Roles Migration
P2P | S1 | 74235 | Accessing or Creating Vendor Data in NetSuite | 191463 | 1 | CA P2P Custom Roles Migration
P2P | S1 | 74182 | PO should have contract # | 191448 | 1.1 | CA P2P Custom Forms Migration
P2P | S1 | 74229 | Projects on Purchase Requisitions | 191448 | 1.1 | CA P2P Custom Forms Migration
P2P | S1 | 74183 | Auto-create PO from approved requisition | 192389 | 1 | CA P2P Requisition and Purchase Order Migration
P2P | S1 | 74180 | Sent PO to a Different Email Address | 192389 | 1 | CA P2P Requisition and Purchase Order Migration
P2P | S1 | 74220 | Purchasing an Item on Behalf of Someone Else | 192389, 191463 | 1 | CA P2P Requisition and Purchase Order Migration, CA P2P Custom Roles Migration
P2P | S1 | 74179 | Electronically deliver PO to vendor | 192389 | 1 | CA P2P Requisition and Purchase Order Migration
P2P | S1 | 74189 | Resending a PO | 192389 | 1 | CA P2P Requisition and Purchase Order Migration
P2P | S1 | 74213 | Notifying the Clarivate Employee of Changes | 192389 | 1 | CA P2P Requisition and Purchase Order Migration
P2P | S1 | 74214 | Withdrawing the Requisition | 192389, 191463 | 1 | CA P2P Requisition and Purchase Order Migration, CA P2P Custom Roles Migration
P2P | S1 | 74157 | Create New Item for Purchase | 191448 | 1.1 | CA P2P Custom Forms Migration
P2P | S1 | 77371 | Vendor Creation by Admin User | 191448 | 1.1 | CA P2P Custom Forms Migration
P2P | S1 | 74181 | Reference PO# on vendor invoice | 191448 | 1.1 | CA P2P Custom Forms Migration
P2P | S1 | 74188 | Purchase Order Squence | NA | NA | NA | Setup manually in FUT
R2R | S1 | 73192 | R2R.218 Script autopopulation of custom segment | 191459, 191476 | 1 | CA R2R Custom Segment Update.docx , CA R2R Custom Return Authorization form.docx
R2R | S1 | 73299 | R2R.226 Admin Add New Center | 191464 | 1 | CA R2R Custom Role.docx
R2R | S1 | 73301 | R2R.228 Admin Edit Center | 191464 | 1 | CA R2R Custom Role.docx
R2R | S1 | 73302 | R2R.229 Admin Edit Locations | 191464 | 1 | CA R2R Custom Role.docx
R2R | S1 | 73303 | R2R.230 Admin Add Location | 191464 | 1 | CA R2R Custom Role.docx
R2R | S1 | 73308 | R2R.234 Admin Add Product Group | 191464 | 1 | CA R2R Custom Role.docx
R2R | S1 | 73309 | R2R.235 Admin Edit Product Group | 191464 | 1 | CA R2R Custom Role.docx
R2R | S1 | 73294 | R2R.221 Admin Create Legal Entity | 191464 | 1 | CA R2R Custom Role.docx
R2R | S1 | 73295 | R2R.222 Admin Edit Legal Entity | 191464 | 1 | CA R2R Custom Role.docx
R2R | S1 | 73982 | R2R.029: Review Company code on Subsidiary |  |  |  | Standard Functionality
R2R | S1 | 73298 | R2R.225 Admin Add New Account | 191464 | 1 | CA R2R Custom Role.docx
R2R | S1 | 73300 | R2R.227 Admin Edit Account | 191464 | 1 | CA R2R Custom Role.docx
R2R | S1 | 73189 | R2R.216 Transaction Types on GL postings | 192386 | 1 | CA R2R JE transaction type, Project type and create plan on revenue fulfillment .docx
R2R | S1 | 73215 | R2R.220 Statistical Accounts Populated |  |  |  | Standard Functionality
R2R | S1 | 77881 | R2R Project Type Attribute | 192386 | 1 | CA R2R JE transaction type, Project type and create plan on revenue fulfillment .docx
R2R | S1 | 78041 | Create Revenue Plans On = Fulfillment | 192386 | 1 | CA R2R JE transaction type, Project type and create plan on revenue fulfillment .docx
R2R | S1 | 76126 | Setup Accounting Segments
R2R | S1 | 76135 | Create Subsidiaries
R2R | S1 | 76133 | Create Accounting Periods
R2R | S1 | 76130 | Setup Chart of Accounts
R2R | S1 | 76751 | Setup Intercompany Accounts
R2R | S1 | 77308 | COA Mapper
R2R | S1 | 73193 | R2R.219 Constant Currency
AR | S1 | 75909 | Standard Sales Order Form | 191450 | 1 | CA AR Forms
AR | S1 | 75822 | Customer Account Management (New Customer) | 191450 | 1 | CA AR Forms
AR | S1 | 75872 | Contact Management (New Contacts) | 191450 | 1 | CA AR Forms
AR | S1 | 75830 | Item Management (New Items- Non Inventory) | 191450 | 1 | CA AR Forms
AR | S1 | 75925 | Setup Customer Payment | 191450 | 1 | CA AR Forms
AR | S1 | 67886 | Reason Code List (Drop Down) | 191450, 191461 | 1 | CA AR Forms, CA AR Roles
AR | S1 | 73083 | Non-Strategic Account Statement Strategy (Notification to Collector 2nd Call Due Date + 35 Days) | 191455, 191461 | 1 | CA AR Non-Strategic Account Statement, CA AR Roles
AR | S1 | 75921 | Invoice Management (Invoice Form) | 191450 | 1 | CA AR Forms
AR | S1 | 75924 | Setup Credit Memo | 191450 | 1 | CA AR Forms
AR | S1 | 68260 | Customer History -Query for Customer (case by case basis) | 191453, 191461 | 1 | CA AR Customer Sales History Saved Search, CA AR Roles
AR | S1 | 68275 | Flagging Promise to Pay on Invoices | 191454, 191461 | 1 | CA AR Flagging Promise To Pay, CA AR Roles
AR | S1 | 67897 | Multi-Select Field Field For Open Invoices on Call Log | 191458, 191461 | 1 | CA AR Open Invoices On Call Log, CA AR Roles
AR | S2 | 67417 | Non-Strategic Accounts Invoice Notification-(Invoice Creation +7 days) |  |  | CA AR Non-Strategic Account Statement
AR | S2 | 63959 | AR-2_2 enable multi-currency |  |  | CA Configurations
AR | S2 | 67421 | Non-Strategic Account Statement Strategy (Notification to Collector- 5 days prior to Due Date ) |  |  | CA AR Non-Strategic Account Statement
AR | S2 | 73572 | Non-Strategic Account Statement Strategy (Notification to Collector to Contact Sales Rep Due Date + 45 Days) |  |  | CA AR Non-Strategic Account Statement
AR | S2 | 73574 | Non-Strategic Account Statement Strategy (Notification to Collector Due Date + 60 Days) |  |  | CA AR Non-Strategic Account Statement
AR | S2 | 67424 | Non-Strategic Account Statement Strategy (First Statement Email on Due Date) |  |  | CA AR Non Strategic Customer Dunning
AR | S2 | 73579 | Non-Strategic Account Statement Strategy (3rd Statement Letter Due Date + 60 Days) |  |  | CA AR Non Strategic Customer Dunning
AR | S2 | 73601 | Non-Strategic Account Statement Strategy (Notification to Collector Third Call Due Date + 65 Days) |  |  | CA AR Non-Strategic Account Statement
AR | S2 | 73881 | Non-Strategic Account Statement Strategy (Suspension Warning Due Date + 75 Days) |  |  | CA AR Non Strategic Customer Dunning
AR | S2 | 74303 | Non-Strategic Account Statement Strategy (Notification to Collector Service Suspension Due Date + 90 Days) |  |  | CA AR Non Strategic Customer Dunning
AR | S2 | 67430 | Non-Strategic Account Statement Strategy (Due Date (+) 15 days) |  |  | CA AR Non Strategic Customer Dunning
AR | S2 | 73079 | Non-Strategic Account Statement Strategy (Notification to Collector First Call Due Date + 25 Days) |  |  | CA AR Non-Strategic Account Statement
AR | S2 | 70662 | Credit Reasons |  |  | CA AR Forms
AR | S2 | 63727 | AR.150: AR-4 Promise To Pay Date Reporting |  |  | CA AR Promise To Pay Date Reporting Saved Search
AR | S2 | 66296 | AR-4 Identifying Strategic Customers |  |  | CA AR Strategic Customers Saved Searches
AR | S2 | 66302 | AR-4 Identifying End Note Dist./Resellers Customers |  |  | CA AR Strategic Customers Saved Searches
AR | S2 | 66677 | Mgr/Supervisor Past due Notification |  |  | CA AR Non-Strategic Account Statement, CA AR Roles
AR | S2 | 63675 | AR.100: Invoice statements |  |  | CA AR Roles
AR | S2 | 63729 | AR.152: AR-4 reports cash projection |  |  | CA AR Saved Searches on Open Invoices
AR | S2 | 63683 | AR.108: Viewing Overdue Balances on the customer Dashboard |  |  | CA AR Saved Searches on Open Invoices
AR | S2 | 69884 | Activate / Deactivate Dunning |  |  | CA AR Non Strategic Customer Dunning
AR | S2 | 63726 | AR.149: Consolidate Accounts Receivable across Clarivate Legal Entities. |  |  | CA AR Saved Searches on Open Invoices
R2R | S2 |  |  |  | 1 | CA R2R Rev Rec Custom fields .docx
R2R | S1 | 73192 | Script autopopulation of custom segment |  | 1.1 | CA R2R Custom Segment Update.docx